## Sheet1
ID | Risks | Probability | Impact | Planning strategy | Actions
1 | Hardware unavailability due to importing delay | Likely | Major | Mitigate | Temporary hardware should be locally rented until new hardware arrives to workspace
2 | Requirement change by the client | Likely | Moderate | Exploit | Client should be required to extend project period and raise project budget to accommodate new changes.
3 | Management change | Rare | Extreme | Mitigate | Old and new management members should attend meetings with other stakeholders to discuss project structure, progress, policies … etc.
4 | tool/software underperformance | Moderate | Major | Avoid | Software tools should be periodically tested and maintained throughout the project