## Project estimation
ID | Tasks | Estimated work hours | Estimated working days (Working day = 5 Hrs) | Cost (Working hour =10$)
Hardware
1 | Maintain Devices | 50 | 10 | 500
2 | Maintain Servers | 20 | 4 | 200
3 | Maintain Routers | 20 | 4 | 200
4 | Update Routing S.W | 5 | 1 | 50
5 | Select suitable UPS | 5 | 1 | 50
Software
6 | Install & update A.V | 10 | 2 | 100
7 | Install / update notepad++ | 5 | 1 | 50
8 | Install / update programming IDE | 20 | 4 | 200
9 | Install / update Testing platform | 30 | 6 | 300
10 | install & setup Configuration management tool | 30 | 6 | 300
Process Design
11 | Design Partner/shop process | 50 | 10 | 500
12 | Design user process | 50 | 10 | 500
13 | Design Maintenance process | 50 | 10 | 500
App Development
14 | Develop & test app functions and logic | 300 | 60 | 3000
15 | Develop & test Partner/shop interface | 100 | 20 | 1000
16 | Develop & test User interface | 100 | 20 | 1000
17 | Develop & test Maintenance Interface | 100 | 20 | 1000
Training
18 | Prepare training material & Software | 30 | 6 | 300
19 | Provide Tools Training | 120 | 24 | 1200
20 | Provide Development Training | 300 | 60 | 3000
21 | Provide Process Training for Shops | 10 | 2 | 100
22 | Provide Maintenance Training | 150 | 30 | 1500
| Total | 1555 | 311 | 15550

## Tools costs
ID | Tool | Supplier | Amount (Units) | Unit price | Cost ($)
Hardware
1 | PCs/Laptops | ASUS | 20 | 600 | 12000
2 | Servers | DELL | 3 | 5000 | 15000
3 | Routers | TP-LINK | 20 | 300 | 6000
4 | UPS units | ABB | 50 | 1000 | 50000
5 | Testing Hardware | Some distributer | 20 | 300 | 6000
Software
6 | Contract with Antivirus supplier | Avast | - | - | 5000
Training
7 | Training Software | CISCO | - | - | 10000
Other
8 | Internet Connection | We | - | - | 3000
| Total |  |  |  | 107000

## Total Costs
Cost Type | Cost ($)
Task Costs | 15550
Tool Costs | 107000
Total | 122550

## Assumptions
Item | Assumptions
PCs/Laptops | Item should have at least the following specifications: -Intel Core i5 11600 Processor -16GB of DDR4 Ram -500GB of storage - 720p webcam
Servers | Item should have at least the following specifications: -100TB of storage per unit - 1Gbps connection - Data loss protection - Data backup reserve
Routers | Item should have at least the following specifications: - 1Gbps Connection - 50m Wireless coverage - Connection Encryption support
UPS units | Item should have at least the following specifications: - Battery capacity that insures 2 hours of working - automatic activation
Testing Hardware | Item should have at least the following specifications: - Arm cortex m3 mcu - 2GB Ram - 250mb Rom