## Sheet1
Project budget =10000 Hrs & num of engineers =5 ….... Assuming each engineer works for 9 hours a day and works 25 days a month. Project period in month = 10000/(9 * 25 * 5 ) = 8.88 month …. Assuming risk tolerance value of 1.22 months Project period = 10 months My current position in project period = 7000 / (9 * 25 * 5 )=6.2 months earned value = 55% * 10000 = 5500 hours Actual cost = 7000 hours Q1: is project over budget? Over budget = 7000-5500 =1500 hours Yes, project is over budget with 1500 hours Q2: is project delayed? planned value = (6.2/10)*10000 = 6200 Yes, project delayed by: 6200 - 5500 = 700 hours Delay in days= 700/(9*5) = 15.5 working days.
| Time in months | planned value | Actual cost | Earned cost
| 1 | 1000 | 1130 | 887
| 2 | 2000 | 2258 | 1774.2
| 3 | 3000 | 3387 | 2661.3
| 4 | 4000 | 4516 | 3548
| 5 | 5000 | 5645 | 4420
| 6 | 6000 | 6774 | 5400
| 6.2 | 6200 | 7000 | 5500
| 7 | 7000 | 7900 | 6200
| 8 | 8000 | 9000 | 7100
| 9 | 9000 | 10160 | 7983
| 10 | 10000 | 11290 | 8871